Minutes Of The Regular City Council Meeting, April 26, 2003, 7:00 P.M. 

“EXHIBIT A”

Projects Update April 2004

By Eddie Peterson
1. 
Downtown Streetscape: The DOT allocated $397,866 for Calhoun's Streetscape project. To date the DOT has paid Valley Crest $321,315 which leaves a balance of $76,551. The remainder of the project includes stamping and coloring of the crosswalks. The local DOT office requires this work to be completed and night. 
2.
McDaniel Station Road: The road improvements are complete and all payments have been made to Northwest Georgia Paving. The project total was $860,513 with $10,000 retainage and an additional $7,662 paid by the IDA for repairs to the south end of the road.  

3. 
Sidewalk Repair: For the past four weeks the Street Department has concentrated on sidewalk repair and section replacements at various locations. 
4. 
Curtis Parkway and Laurel Lane Signal: Signal equipment has been ordered and design plans should be complete by May 7, 2004. At that point we will bid the project and begin some property acquisition. The project will include signalization, turn lanes, radius widening, passing lane, and stripping. 
5. 
Creekview Drive School Access: A copy of the property appraisal was received by Mr. Walter Hackett on April 23, 2004. Mr. Hackett said he would be in Calhoun the third week of May to discuss Calhoun’s street requirements for access into the new school.  At that time we will need to make a final offer because of time limitations. 
6. 
Swimming Pool Restroom Renovations: The renovations are on schedule and should be complete by the second week of May 2004. This will allow the pool to open by mid-May 2004. 
7. 
Signal Equipment: Signal equipment for the intersection of SR 136 and Sr 156 connector at the National Guard Armory has been ordered and should arrive by late May 2004. 
8. 
Recreation SPLOST: We will be working on plans for the tennis complex and lighting of two soccer fields during the next several weeks. At the present time Recreation SPLOST monies are at $600,000 for disbursement. Monthly SPLOST recreation revenues for the City of Calhoun are in the $60,000 range. 
9. 
North Calhoun By-Pass Study: Met with GDOT Planners on April 19, 2004 to discuss North Wall Street from Line Street to Red Bud Road. They had requested our 1992 Transportation Study for review and wanted our feelings on certain traffic flows. The latest time table for the study completion is May 2004. I got feeling during the meeting that GDOT had concentrated on a by-pass more than widening North Wall Street. When we receive the study a trip to meet with Commissioner Linnenkohl might be worthwhile. 

