City of Calhoun

West End Revitalization Initiative- phase I

Community Development Block Grant Program

Project Completion Public Hearing

McConnell Road Community Center

October 17, 2011, 6:00p.m.

Present:	James F. Palmer, Mayor

Al Edwards, Mayor Pro Tem

Bill Bailey, City Attorney

Joey Moore, Community Development

Derrall Culberson, Finance

Paul Worley, Deputy Clerk

Angela Steedley, grant administrator, Steedley Firm

- Mayor Palmer opened the public hearing and welcomed everyone in attendance.

- Mayor Palmer reviewed some of the results of the West End Revitalization project.

  - The City of Calhoun received $800,000 in a Community Development Block Grant on September 16, 2008 to upgrade water and sewer infrastructure and improve housing conditions as part of its Phase I West End Neighborhood Revitalization.

- The following is a review of the amount of funds for each activity and amount that benefited low and moderate income persons.

  - H.001.01 $162,665 was awarded to acquire six properties.  Of these six, only two were acquired (116 McConnell Road and 617 Martin Luther King Jr. Boulevard).

    - $43,385.41 was expended: $8,435.41 for legal fees, $7,725.00 for appraisals, $12,338.00 to acquire 116 McConnell Road, and $14,887.00 to acquire 617 Martin Luther King Jr. Boulevard.  The City of Calhoun provided approximately $9,200 cash and in-kind to raze and dispose of respective structures.

    - 608 Court Street could not be acquired, as the appraisal price did not support the purchase price.

    - 705 Court Street could not be acquired or demolished at the request of the owner, who seeks financing for the balance of reconstruction.

    - 714 Court Street was ineligible for acquisition due to title issues.

    - 710 Martin Luther King Boulevard was also ineligible for acquisition due to title issues.

  - H.008.00- $16,094 was awarded to accommodate the temporary relocation of four households.  A total of $1,746.25 was expended for temporary relocation expenses associated with the rehabilitation of 118 McConnell Road.

  - C.022.00- $66,400 was awarded for contingencies.  $33,834 of this amount was transferred to public facilities P.03J.02, which increased from $338,384 to $372,218 for sewer improvements and road repair associated therewith.  A total of 112 people, 94 of whom qualify as low and moderate income benefited from this activity.

  - H.14A.01- $62,482 was awarded to rehabilitate three houses (118 McConnell Road, 722 Martin Luther King, Jr. Blvd, and 100 Neal Street).  $46,969.35 was utilized to rehabilitate 118 McConnell Road upon DCA approval of a request to exceed maximum.  As explanation, the bids received were 20 percent greater than the original cost estimate, and lead abatement was required.  A standard sum of $2,500 in CDBG funds was also expended for project delivery costs.  Two low-income persons benefited from this activity.

    - The homeowner at 722 Martin Luther King, Jr. Blvd voluntarily decided not to participate.

    - The homeowner at 100 Neal Street was permanently relocated to a nursing home.

  - H.14A.02- $97,975 was awarded to raze and reconstruct the home at 112 Harkins Street.  Unfortunately, the property became disqualified to participate in the program due to a change of ownership.

  - A.21A.00- $56,000 was awarded and expended in CDGB funds for grant administration activities.  An additional $29,490.00 was contributed by the Steedley Firm as goodwill toward the project for services performed September 16, 2010 through September 30, 2011.

- There is a final quarterly report available for review and comment.  In summary, the City expended $532,481.53 in CDGB funds, $541,892.18 in local cash, and $137,675.20 in in-kind time toward the project.  Calhoun Affordable Housing also expended considerable in-kind time to make the project a success.

- The meeting was adjourned.