MEETING MINUTES AND AGREEMENT

A meeting was held on Wednesday, July 29, 2015 at the offices of the Gordon County Chamber of Commerce located at 300 S. Wall Street, Calhoun, Georgia for the purposes of discussing a dedicated water supply for fire suppression and construction permitting at the facilities of LG Hausys America, Inc. located at 310 LG drive in Gordon County, Georgia.

The following were in attendance at the meeting: LG Hausys America, Inc. was represented by Jesu Moon, Plant Manager LG Hausys America, Inc. – Georgia Plant, T. K Ahn, CFO, Sang Lee, Dowon (Steve) Kang, Jaye Lee, its engineer Jeff Hewitt of American Fire Protection, Inc. and others; the City of Calhoun was represented by the Hon. Jimmy Palmer, Mayor, Larry Vickery of public works and Jerry Crawford of water and sewer; Gordon County was represented by John King, County Administrator, Joey Jordan, Fire Department, Mike Fowler, Office of Building Inspector and Jim Ledbetter, County Attorney; the Development Authority of Calhoun and Gordon County Georgia was represented by Kathy Johnson, Director and Bill Thompson, its attorney; the State of Georgia was represented by Lindsay Martin.

Upon calling the meeting to order, a discussion ensued regarding the requirements of a dedicated water supply for fire suppression at the buildings and campus of LG facilities in Gordon County, Georgia. The general concern with the existing water supply is that the LG property and Mohawk are served by a 1,000,000 gallon water tank for both potable water and fire suppression and this tank fluctuates in its capacity. In order to assure a constant available water supply for fire suppression, Gordon County and fire codes require an assured and dedicated water source. After a discussion of alternatives, the representatives of all entities present agreed that either of two alternatives would be sufficient to meet the water supply requirements for fire suppression as required by the applicable codes as follows:

- The City of Calhoun suggested that a new potable water line could be installed from Old Dixie Highway to the LG facilities and along Raymond King Drive to Mohawk facilities which would allow the existing water tank serving LG and Mohawk to be used as a dedicated water supply for fire suppression that would not be subject to fluctuation of water level. The cost of installation of the water lines to Mohawk and LG would be paid by LG Hausys America, Inc. not to exceed $100,000. Agreements, approval, and arrangements must be obtained from and between the proper representatives of the parties regarding issues of title, maintenance of the water tank, easements and other issues. LG will pay a tank maintenance fee of $10,000 per year to the City of Calhoun; or

- All parties agree that option one above is preferred by LG and agree to pursue option one in good faith. In the alternative, LG recognizes and understands the requirement for a dedicated water supply and covenants and agrees that if, after good faith efforts, option one is not feasible for any reason, it will install a dedicated water tank for fire suppression needs at its facilities while reserving the opportunity to request assistance from others for funding sources or land for construction of the dedicated water tank upon an express written agreement. This reservation of right to discuss funding and land creates no obligation on any party, but, reflects the desire of LG to request assistance in the future.

Upon execution of this agreement, Gordon County will issue temporary permits to LG for construction of foundations and piers.

In Witness Whereof, the parties evidence their agreement by their signatures affixed below on the ______ day of _______________, 2015

LG Hausys America, Inc. by:			City of Calhoun by:

________________________			______________________

Jesu Moon, Plant Manager			Jimmy Palmer, Mayor

Plant Manager LG Hausys America, Inc. 	City of Calhoun

Georgia Plant

Gordon County, Georgia by:			Development Authority by:

_________________________			_______________________

John King, Administrator				Kathy Johnson, Director